## Material Order (BoM)
Estimasi BOQ Ventilator (include Fluke)
No | Item | Spesifikasi | Jumlah | Unit | Harga | Total | Referensi
PENGEMBANGAN SISTEM GERAK DAN MOTOR (SISTEM MEKANIK VENTILATOR) | [5 empty] | 50000000
1 | Sistem Mekanik & Customize | - Linear Guide - Linear Block - Timing Pulley - Timing Belt - Lengan Penekan - Base - Baki - Motor Holder - Bolt Screw - Nut - Baut,Mur,dll | 1 | set | 25000000 | 25000000 | Estimasi Biaya Mekanik
2 | Motor Servo | Delta Servo 1,5 kW | 1 | set | 25000000 | 25000000 | PT Delta
PENGEMBANGAN BREATHING SYSTEM | [5 empty] | 7135000
1 | Flow Sensor Hamilton (Tubing) | Support Mesin Ventilator : Type : Adult/Pediatric Galileo/Raphael/C1/T1/MR1/C2/C3 | 1 | pcs | 750000 | 750000 | https://tokopedia.link/m18e7W5Vjbb
2 | PEEP Valve | PEEP(Positif End Expiratory Pressure) VALVE | 1 | pcs | 1400000 | 1400000 | https://tokopedia.link/A1IRCEcWjbb
3 | Reusable Resuscitator (Ambu Bag & Accesorries) | - Resuscitator silicon bag x 1pc - Reservoir bag x 1pcs - 02 tubing x 1 pcs '- Mask x 1 pcs - Airway x 3 size 1 pcs each - 1 carry case | 1 | pcs | 750000 | 750000 | https://tokopedia.link/8MXMOnuWjbb
4 | Breathing Circuit | Breathing Circuit Ventilator Kelengkapan -Circuit -Chamber -Water Trap -Heater wire -Connector | 1 | set | 550000 | 550000 | https://tokopedia.link/PSInVTSYjbb
5 | Oxygen supply (Tabung) | - Cylinder Tank Ocygen - Furemed Oxygen Regulator - F roda Oxygen CAT - Hospitech Oxygen tubing conn | 1 | set | 1185000 | 1185000 | Sakura | Perlu ditambahkan aksesoris: 3D printing, dsb
6 | Accessories (3 D Printing, Selang Tambahan) |  | 1 | lot | 2500000 | 2500000
PENGEMBANGAN SUPPORT DAN CASING | [5 empty] | 7200000
1 | Casing | Bahan akrilik | 1 | unit | 1700000 | 1700000 | PO Cipta Jaya Acrilic
2 | Meja Lemari | Bahan Stainless | 1 | unit | 4500000 | 4500000 | PO Biru Karya pratama
3 | Accessories (Peredam Suara & Getaran) | Busa , bahan peredam lainnya | 1 | lot | 1000000 | 1000000
PENGEMBANGAN RANGKAIAN ELEKTRONIK (SISTEM KONTROL VENTILATOR) | [5 empty] | 213923900
1 | XL4015 DC-DC Step Down | Variant : Standard ¦ Extra Adjustable Current ¦ Extra Voltmeter Input Voltage : 4 ~ 38 V Adjustable Output Voltage : 1.25 ~ 36 V Output Current : 5A Efficiency : max. 96% Operating Frequency : 180 kHz Operating Temperature : -40° ~ 85° C | 1 | pcs | 25900 | 25900 | https://tokopedia.link/8o8zMv7Ujbb
2 | Limit Switch CM-1703 | CM Micro Switch Type : CM-1703 Merk : Fort | 2 | pcs | 25000 | 50000 | https://tokopedia.link/tyngZXiVjbb
3 | Arduino Nano + Kabel | Features: Blue board. Digital I O Pins: 12 (D2 D13) Analog Input Pins: 8 (A0 A7) 1 Pair TTL serial data receiving and transmitting pins: RX TX PWM Output Pins: 6 (D3 D5 D6 D9 D10 D11) Microcontroller: Atmel Atmega328P AU Employs Atmega328P AU single chip Supports USB download and power supply ISP download Supports external 5V 12V DC power supply or 9V battery Comes with cable length: 25cm | 2 | pcs | 50000 | 100000 | https://tokopedia.link/wg7CSvlWjbb
4 | Raspberry 4 Model B | Broadcom BCM2711, Quad core Cortex-A72 (ARM v8) 64-bit SoC @ 1.5GHz 4GB LPDDR4-3200 SDRAM (depending on model) 2.4 GHz and 5.0 GHz IEEE 802.11ac wireless, Bluetooth 5.0, BLE Gigabit Ethernet 2 USB 3.0 ports; 2 USB 2.0 ports. Raspberry Pi standard 40 pin GPIO header (fully backwards compatible with previous boards) 2 × micro-HDMI ports (up to 4kp60 supported) 2-lane MIPI DSI display port 2-lane MIPI CSI camera port 4-pole stereo audio and composite video port H.265 (4kp60 decode), H264 (1080p60 decode, 1080p30 encode) OpenGL ES 3.0 graphics Micro-SD card slot for loading operating system and data storage | 1 | pcs | 819000 | 819000 | https://tokopedia.link/Xeqzj8DWjbb
5 | Micro SD | Sandisk MicroSD Ultra UHS-1 A1 64GB Up To 100MB/s Non Adapter | 1 | pcs | 190000 | 190000 | https://tokopedia.link/fHtZwNSWjbb
6 | LCD Display 7" | 7" Touch Dimension: 194mm x 110mm x 20mm Resolution: 800 x 480 10 points Capacitiv | 1 | pcs | 1125000 | 1125000 | https://tokopedia.link/IXEFI5YWjbb
7 | ADS 1115 16 bit ADC | Wide Supply Range : 2.0V to 5.5V Low Current Consumption: Continuous Mode : Only 150'A Single-Shot Mode: Auto Shut-Down Programmable Data Rate : 8SPS to 860SPS Internal Low-Drift Voltage reference Internal Oscillator Internal PGA I2C INTERFACE : Pin-Selectable Addresses Four Single-Ended or Two Differential Inputs Programmable Comparator This board/chip uses I2C 7-bit addresses between 0x48-0x4B, selectable with jumpers | 1 | pcs | 31000 | 31000 | https://tokopedia.link/GMrdyM6Wjbb
8 | Block Terminal AC | - Terminal Block - Terminal block ground rail - Stopper block - Tutup terminal block - Din rail MCB - Fuse Holder - Fuse kaca - Seal silicon ventilator - kontaktor 40A - MCB 20A 2 pull - Jumper terminal block | 1 | set | 3000000 | 3000000 | Cikapundung
9 | Sensor MPXV7002DP | Features: - -2 to 2 kPa (-0.3 to 0.3 psi). - 0.5 to 4.5 V Output Weight: 0.1 oz; 4 g | 1 | pcs | 450000 | 450000 | https://tokopedia.link/CzaTtwJXjbb
10 | IC 7404 Inverter | - Terdiri dari 6 unit inverter atau NOT. - Family ACT (advanced CMOS and TTL compatible) memiliki rise time dan fall time yang lebih cepat dari pada family CMOS (CD, HC, HCT) dan TTL (SN, 74xx) biasa - Cocok untuk aplikasi frekuensi tinggi - Vcc : 5 volt - Mampu drive beban 50 ohm - Package: SOIC / SOP 14 pin | 2 | pcs | 12500 | 25000 | https://tokopedia.link/M2j30QZXjbb
11 | IC Optocoupler | - 16 dip optocoupler CNY74-4 | 2 | pcs | 17500 | 35000 | https://tokopedia.link/3Gkrd3cYjbb
12 | Kabel Pelangi 50 pin | Tipe: kabel pita pelangi AWG: 28 Jumlah kaki: 50 | 5 | meter | 85000 | 425000 | https://tokopedia.link/IT0KvSiYjbb
13 | Power Supply 12V 5A | Input Power: 110VAC-220VAC 1PH Output Voltage: 12VDC Rated Current: 5A (Pure) Dimensi: 11cm x 7.7cm x 3.7cm | 1 | pcs | 35000 | 35000 | https://tokopedia.link/N8grJ5sYjbb
14 | DS3231 RTC module | The 1.-40 ° C to +85 ° C temperature range, timing accuracy kept at ± 5ppm (± 0.432 sec / day) 2 timed to provide continuous battery backup 3 low-power 4. Device package and function compatible with the DS3231 5. Complete clock calendar functions include seconds, minutes, hours, day, date, month and year timing and provide valid until the year 2100 leap year compensation 6 two calendar alarm 7.1Hz and 32.768kHz output 8 Reset button debounced input and output 9-speed (400kHz) I2C serial bus 10. +2.3 V to +5.5 V Supply Voltage 11 ± 3 ° C accuracy digital temperature sensor 12.-40 ° C to +85 ° C operating temperature range 13.16-pin SO (300mil) package 14 by Underwriters Laboratories (UL) certification | 1 | pcs | 20000 | 20000 | https://tokopedia.link/rUZYjkDYjbb
15 | MPX5700AP (Flow Sensor -->elektronik ) | Model: MPX5700AP Brand: Freescale Freescale Function: MPX5700: 0 to 700kPa, differential, gauge and absolute pressure, integrated pressure sensor Package: in- pressure sensor Condition: 100% brand new original authentic | 1 | pcs | 293000 | 293000 | https://tokopedia.link/L5T2etKYjbb
16 | KE-25 Oxygen Sensor | * Long life - 2.5~10 years in ambient air * Virtually no influence from CO2, CO, H2S, NOx, H2 * Low cost * Operates in normal ambient temperatures * Stable output signal * No external power supply required for sensor operation * No warmup time is required | 1 | pcs | 2300000 | 2300000 | https://tokopedia.link/IFoE1exVjbb
17 | Kalibrator | Fluke Gas Analyzer VT650 | 1 | unit | 180000000 | 180000000 | Estimasi (Jika beli baru)
18 | Accessories | - Resistor - PCB - Tombol ON/OFF - Emergency Button - Konektor Selang - Selang bening - White Housing Male/Female - Solder - Timah Solder - Foam Double Tape - Kipas Pendingin - Kabel Jumper Tunggal - Casing Raspberry - Socket IC - Transistor Switch - Male/Female Pin Header | 1 | set | 25000000 | 25000000 | Estimasi Biaya Aksesoris
PENGEMBANGAN BACKUP POWER | [5 empty] | 20000000
1 | UPS 3000V (Included Batere) | APC | 1 | set | 20000000 | 20000000 | Estimasi
ESTIMASI TOTAL MATERIAL VENTILATOR | [5 empty] | 298258900
Notes : (Additional Berdasarkan Proposal)
1 | Humidifier | Mekanik (Breathing System) | 1 | set | 2000000 | 2000000 | Estimasi
2 | CO2 | Sensor (System Kontrol ) | 1 | set | 3000000 | 3000000 | Estimasi
3 | Exhalation Valve |  | 1 | set | 2000000 | 2000000 | Estimasi
4 | Servo Valve | Valve (System Kontrol ) | 1 | set | 2000000 | 2000000 | Estimasi
9000000

## Timeline Riset Ventilator
TIMELINE
VENTILATOR RESEARCH
No | Description | Personil | Duration |  | M1 |  |  |  | M2 |  |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  |  | M6 |  |  |  | M7 |  |  |  | M8 |  |  |  | M9
[5 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W23 | W24 | W25 | W26 | W23 | W24 | W25 | W26 | W23 | W24 | W25 | W26
[5 empty] | 31-6 | 7-13 | 14-20 | 21-27 | 28-4 | 5-11 | 12-18 | 19-25 | 26-1 | 1-7 | 8-14 | 15-21 | 22-28 | 29-5 | 6-12 | 13-19 | 20-26 | 27-3 | 4-10 | 11-17 | 18-24 | 25-31 | 1-7 | 8-14 | 15-21 | 22-30 | 1-7 | 8-14 | 15-21 | 22-30 | 1-7 | 8-14 | 15-21 | 22-30 | 1-7 | 8-14 | 15-21 | 22-30
PERANCANGAN DESAIN & DEVELOPMENT VENTILATOR
A | PENGEMBANGAN SISTEM GERAK DAN MOTOR (SISTEM MEKANIK VENTILATOR) | PENELITI, QC/QA, SYS E, SE, ELEC E | 12 | weeks | bar: M1 W1 to M3 W12
1. Rancangan Desain Rangka & Mesin Ventilator | bar: M1 W1 to M1 W4
2. Penyusunan sistem gerak dan motor
Pengadaan peralatan sistem motor | bar: M1 W1 to M2 W8
Pengadaan peralatan aksesoris breathing system | bar: M1 W1 to M2 W8
3. Pembuatan / manufakturing kerangka mekanik | bar: M2 W5 to M2 W8
3. Pembuatan support dan casing
Pengadaan peralatan casing | bar: M2 W9 to M3 W12
B | PENGEMBANGAN SISTEM KONTROL VENTILATOR | PENELITI, QC/QA, SYS E, SE, ELEC E | 18 | weeks | bar: M1 W1 to M5 W20
1. Pengembangan rangkaian elektronik
| Pengadaan rangkaian elektronik |  | 8 | weeks | bar: M1 W1 to M2 W8
| Survey terkait servo valve tanpa pelumas (medical grade) |  | 8 | weeks | bar: M1 W1 to M2 W8
| Cetak dan merangkai rangkaian elektronik |  | 3 | weeks | bar: M1 W1 to M3 W10
2. Pemprograman kontrol Ventilator
1. Pengembangan program deteksi sensor
| Test dan Kalibrasi sensor Pressure |  | 3 | weeks | bar: M1 W4 to M2 W8
| Test dan Kalibrasi sensor Flow |  | 3 | weeks | bar: M1 W4 to M2 W8
| Test dan Kalibrasi sensor O2 |  | 3 | weeks | bar: M1 W4 to M2 W8
| Test dan Kalibrasi sensor CO2 |  | 3 | weeks | bar: M1 W4 to M2 W8
| Test dan kalibrasi algoritma integral Volume |  | 3 | weeks | bar: M1 W4 to M2 W8; M3 W11 to M3 W13
| Test dan Kalibrasi algoritma IPP, PIP, PEEP |  | 3 | weeks | bar: M1 W4 to M2 W8; M3 W11 to M3 W13
| Test dan Kalibrasi algoritma IE dan RR |  | 2 | weeks | bar: M1 W4 to M2 W8; M3 W11 to M3 W12
| Test dan Kalibrasi algoritma trigger napas |  | 2 | weeks | bar: M1 W4 to M2 W8; M3 W11 to M3 W12
| Test dan Kalibrasi algoritma Lung Compliance |  | 2 | weeks | bar: M1 W4 to M2 W8; M3 W12 to M3 W13
| Test dan Kalibrasi algoritma kontrol O2 mixture valve |  | 2 | weeks | bar: M1 W4 to M2 W8; M3 W12 to M3 W13
| Test dan Kalibrasi algoritma kontrol dan display PEEP |  | 2 | weeks | bar: M1 W4 to M2 W8; M3 W13 to M4 W14
| Test dan Kalibrasi Humidifier |  | 2 | weeks | bar: M1 W4 to M2 W8; M3 W13 to M4 W14
2. Pengembangan program alarm
| Alarm 1: Trigger Napas |  | 2 | weeks | bar: M2 W5 to M2 W9; M3 W13 to M4 W14
| Alarm 2: Over Pressure |  | 2 | weeks | bar: M2 W5 to M2 W9
| Alarm 3: Low PEEP |  | 2 | weeks | bar: M2 W5 to M2 W8; M4 W14 to M4 W15
| Alarm 4: O2 Tolerance |  | 2 | weeks | bar: M2 W5 to M3 W11
| Utilitas Alarm (Prioritas, Reset, Mute) |  | 2 | weeks | bar: M2 W5 to M2 W9; M4 W15 to M4 W16
3. Pengembangan program aktuator motor
| Pengujian & kalibrasi awal motor servo |  | 2 | weeks | bar: M1 W2 to M1 W3; M2 W7 to M3 W12
| Mandatory Volume |  | 2 | weeks | bar: M2 W7 to M3 W12; M4 W14 to M4 W15
| Assisted / Trigger Volume |  | 3 | weeks | bar: M2 W7 to M3 W12; M4 W14 to M4 W16
| Mandatory Pressure |  | 3 | weeks | bar: M2 W7 to M3 W12; M4 W17 to M5 W19
| Assisted / Trigger Pressure |  | 3 | weeks | bar: M2 W7 to M3 W12; M5 W18 to M5 W20
| Algoritma Safety (integrasi dengan program alarm) |  | 2 | weeks | bar: M2 W7 to M3 W12; M4 W16 to M4 W17
| 4. Pengembangan program dashboard |  | 4 | weeks | bar: M2 W9 to M3 W12
| 5. Pengembangan program data |  | 4 | weeks | bar: M3 W11 to M4 W14
C | PENGEMBANGAN SISTEM POWER SUPPLY (BACKUP BATTERY) | QC/QA, SYS E, ELEC E | bar: M2 W7 to M2 W8
| Pengadaan peralatan UPS (Termasuk Battery) |  | 2 | weeks | bar: M2 W7 to M2 W8
D | INTEGRASI SYSTEM | QC/QA, SE, SYS E | bar: M2 W9 to M5 W20
| 1. Integrasi sistem mekanik dengan sistem power supply |  | 12 | weeks | bar: M2 W9 to M5 W20
| 2. Integrasi sistem kontrol dengan sistem mekanik ventilator |  | 12 | weeks | bar: M2 W9 to M5 W20
PENGETESAN PROTOTYPE (INTERNAL TEST) | bar: M5 W21 to M7 W24
E | 1. Functional Test & Fixing Problems (Mekanik Fungsional) | PENELITI, QC/QA, SE, SYS E, TECH W | 4 | weeks | bar: M6 W25 to M7 W24
| 2. Functional Test & Fixing Problems (Desain & System Fungsional) | PENELITI, QC/QA, SE, SYS E, TECH W | 4 | weeks | bar: M5 W21 to M6 W24
PENGETESAN FINAL PRODUK (BPFK atw Lainnya) | bar: M7 W25 to M8 W24
F | Performance Test & Repair (All system) | PM, QC/QA, PENELITI, SE, SYS E | 4 | weeks | bar: M7 W25 to M8 W24
PELAPORAN FINAL | bar: M6 W23 to M9 W26
G | Pembuatan Laporan Final & Drawing | QC/QA, PENELITI, SYS E, TECH W | 16 | weeks | bar: M6 W23 to M9 W26
= Baru / Tambahan Fitur

## Action Plan
ACTION PLAN
DEVELOPMENT DRONE AUTONOMOUS
No. | Action Plan | [8 empty] | PIC | TARGET | STATUS
PERANCANGAN DESAIN & DEVELOPMENT VENTILATOR
1 | Rancangan Desain Rangka & Mesin Ventilator | [8 empty] | SAM | 4 Weeks | NEXT ACTION
2 | Melakukan Procurement (ORDER # 1) :--->MOS | [8 empty] | AAZ, SAM, HAM | M1-M2 ( …..... 2021 ) | NEXT ACTION
PENGEMBANGAN SISTEM GERAK DAN MOTOR (SISTEM MEKANIK VENTILATOR)
PENGEMBANGAN BREATHING SYSTEM
PENGEMBANGAN RANGKAIAN ELEKTRONIK (SISTEM KONTROL VENTILATOR)
3 | Melakukan Procurement (ORDER # 2) :---->MOS | [8 empty] | AAZ, SAM, HAM | M2 ( …...... 2021 ) | NEXT ACTION
PENGEMBANGAN SUPPORT DAN CASING
PENGEMBANGAN BACKUP POWER
Accessories for Ventilator Installation
3 | Melakukan Development Research (Assembly, Programming & Functional Test) :
1. Penyusunan sistem gerak dan motor :
| 1. Desain Model & Rangka Mekanik Ventilator | [8 empty] | SAM, HAM |  | NEXT ACTION
| 2. Merakit Motor & Komponen Penunjang lainnya | [8 empty] | SAM, HAM |  | NEXT ACTION
| 3. Basic Functional Test & Fixing | [8 empty] | SAM, HAM |  | NEXT ACTION
| 2. Melakukan Pengembangan Sistem Kontrol | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level) | 2. Assembly Stage 2 ( High Level)
| 1. Pengembangan program deteksi sensor | [8 empty] | HAM |  | NEXT ACTION
| 2. Pengembangan program alarm | [8 empty] | HAM |  | NEXT ACTION
| 3. Pengembangan program aktuator motor | [8 empty] | HAM |  | NEXT ACTION
| 4. Pengembangan program dashboard | [8 empty] | HAM |  | NEXT ACTION
| 5. Pengembangan program data | [8 empty] | HAM |  | NEXT ACTION
6. Pengadaan rangkaian elektronik
5 | Melakukan Fuctional Test & Fixing Problems | [8 empty] | SAM, HAM |  | NEXT ACTION
6 | Melakukan Integrasi System :
| 1. Integrasi sistem mekanik dengan sistem power supply | [8 empty] | SAM, HAM |  | NEXT ACTION
| 2. Integrasi sistem kontrol dengan sistem mekanik ventilator | [8 empty] | SAM, HAM |  | NEXT ACTION
7 | Internal Test & Repair (All system) --> Performance Test (Drone) | [8 empty] | SAM, HAM |  | NEXT ACTION
8 | Pembuatan Laporan Final & Drawing | [8 empty] | HAM |  | NEXT ACTION